## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-002 | Introduction to Project(Gen AI Powered Customer Support Quality Auditor ) | MUST HAVE | No Dependency | janani , priya | completed
S1 | S1 | US-002 | Workfow Creation And Project Goal Document | MUST HAVE | No Dependency | janani, Priya | completed
S2 | S2 | US-002 | About The Agile Sheets | MUST HAVE | No Dependency | janani ,Priya | completed
S2 | S2 | US-002 | Analyzing The Requirements Of project,uses and outcomes of the Project | MUST HAVE | No Dependency | janani, Priya | completed
S3 | S3 | US-002 | searching The Correct prepocessed Dataset suitable for project | SHOULD HAVE | kaggle | janani,Priya | Completed
S3 | S3 | US-002 | Downlad the libraries Uses for project | MUST HAVE | whisper AI | janani,Priya | Completed
S4 | S4 | US-002 | Gathering The Required Resources for Project | SHOULD HAVE | RAG PIPELINES | janani,Priya | completed
S5 | S5 | US-002 | presentation of milestone 1 ( Audio Transcripts) | MUST HAVE | No Dependency | janani,Priya | Completed
S6 | S6 | US-002 | Presentation of milestone 2( Scoring of empathy ,Compliance) | MUST HAVE | sentiment analysis | janani,Priya | completed
S7 | S7 | US-002 | Presentation Of milestone 3(Creating Dashboard of Scoring) | MUST HAVE | pinecone | janani,Priya | completed
S8 | S8 | US-002 | Presentation Of milestone 4( Connecting With Database and UI/UX | MUST HAVE | UI/UX | Janani,Priya | completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 57 | 17 | 15 | 7 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
SPRINT 1 BACKLOG
US-002 | 1 | Introduction To Project (Gen AI Powered Customer Support Quality Auditor | 24-12-2025 | 24-12-2025 | janani, priya | understanding | completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | workflow Creation And Project goal Document | 25-12-2025 | 25-12-2025 | janani, priya | understanding | completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 3 | ABout The Agile Sheets | 26-12-2025 | 26-12-2025 | janani, priya | understanding | completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 4 | Analyzing The Requirements Of Project &uses | 29-12-2025 | 31-12-2025 | janani, priya | identifying and searching | completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 5 | searching The correct Preprocessed Dataset Suitable for project | 2-01-2026 | 09-01-2026 | janani, priya | downloading | completed | 7 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 6 | downlload the libraries uses for Project | 10-01-2026 | 17-01-2026 | janani, priya | downloading | completed | 7 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 7 | Gathering the Required Resources for project | 18-01-2026 | 25-01-2026 | janani, priya | abstract | completed | 7 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 8 | presentation of Milestone 1( Audio Transcripts ) | 27-01-2026 | 02-02-2026 | janani, priya | processed And Presentation | completed | 8 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 9 | presentation Of milestone 2( Scoring Of Empathy Conpli | 03-02-2026 | 10-02-2026 | janani, priya | scoring &Presentation | Completed | 7 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 10 | presentation Of milestone 3 (Creating Dashboard of Scoring ) | 11-02-2026 | 17-02-2026 | janani, priya | dashboard & Presentation | Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 11 | presentation of milestone 4( connecting with databsdatabase and UI/UX) | 18-02-2026 | 23-02-2026 | janani, priya | interface and database | completed | 5 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
sprint 1 | Day 2 | Lack Of Clarity on Project requirements | Mentor &Team Discussion
sprint 1 | Day 4 | lack of clarity on specific Project goals | analyzing project keypoints
sprint 2 | Day 6 | Agile Template Confuse | reference one- doubts clear
sprint 2 | Day 8 | identifying dataset for project | lot of search & Guidance
sprint 3 | Day 10 | resources for the building of project | understanding Requirements
sprint 4 | Day 15 | scoring of empathy ,compliance | Clear Audio Transcripts
sprint 4 | Day 20 | Rag Pipelines with pinecone & langchain | Database Management
sprint 5 | Day 25 | connecting with UI/UX | without disturb previous code

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 26/12/2025 | 24/01/2026 | Siva Priya | presentation | corrections | active Participant | corrected Through Mentor
2 | sprint 2 | 25/01/2026 | 23/02/2026 | Janani | coding | Nothing | Active Participant | performed well